Workshop or Program Checklist

What is the nature of the program or workshop?

What is the purpose?

Whose is the target audience?

Is it physical or virtual (or a combination)?

Key elements of the program or the workshop

How long is the program

Promotion

Where are you promoting (make a list of prospective place or people who can promote it)?

What is the nature of the promotion (Facebook ads, emails, flyer)

What is the timing: Set the timing for each step of the promotion.

Start date of the program (include time if applicable)

Start date of the promotion

Early bird end date

Registration end date

Pre-Planning: Before you launch the promotion make a list of what you need to do?

Design of the program or workshop: List how many sessions and what is covered – full outline which can be the basis for your promotional material

State exactly what each participant will do and receive in the program – set out the timing of each element – is it a weekly program? Then what do they do each week.

Set dates for developing materials and program or workshop design - Do a timeline – work backwards from the start date of the program or workshop – Do this at the end when you have a full plan

Materials – What do you need?

List:

What do you need to create these materials: (Be sure to state how long each one will take to create)

Research information for the workshop or program?

Graphic designer for a flyer?

Powerpoint

Handouts? List what is in the handout – make sure it gives them something to do when they go home

Recipes?

Menu plans?

Exercises to do during the meeting?

Survey or quiz?

Logistics (for live workshop or program)

Location:

Time:

Layout each meeting: List the order of each activity and how long each will take:

Example: Introduction: 10 minutes

Present educational piece: 40 minutes

Demonstrate recipe: 20 minutes

Serve food: 20 minutes

Take questions: 30 minutes

Remember: Nothing ever times as you plan it – so leave extra time for when things go long and have an extra activity for when things run short

Make a list of materials and ingredients that are needed for each element of the program

Go back and assign a budget for each activity that has been listed. This is for an actual cost money you will spend and not your time.

Save all receipts so actual costs can be calculated. Use the Project Budget Tool Excel spreadsheet to input calculate your costs and profit potential. List the results

Profit Potential

Revenue:

Expenses:

Net Profit:

Shopping List: Use the Food Ingredient or Material Calculation List – use this to make a shopping list for what you have to buy

Planning for the Day of the Event:

List everything you need for the day of the program or workshop (such as handouts, samples you may have to give out, food items you may prepare to serve, power point. Pick the day in you mind and go step by step through the workshop. Write done everything you may need, pens, paper, serviettes, plates, glasses, a sheet for collecting emails. You will use this list to have everything ready if you are doing it in your home or to pack your car if you are doing it in another location. Go over this list the night before to make sure everything is account for. Then use this list to organize everything before the event if it is your home or loading your car- checking off each item as you go.